## Project Planner
PurpleAir Monitoring Gant Chart
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 2 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START (Week Started?) | PLAN DURATION (How Many Weeks Will It Take?) | ACTUAL START (Week Started?) | ACTUAL DURATION (How Many Weeks Did It Take?) | PERCENT COMPLETE | PERIODS (Weeks)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Training | 1 | 2 | 1 | 2 | 100%
Interpreting Programs | 1 | 3 | 1 | 2 | 100%
Documentation of Interpretation | 1 | 4 | 1 | 4 | 100%
Design Testing Environment | 5 | 2 | 2 | 3 | 75%
Deploy Testing Environment | 5 | 2 | 3 |  | 60%
Analyize Testing Environment | 5 | 3 |  |  | 0%
Debug Testing Environment | 7 | 2 |  |  | 0%
Design Automation | 8 | 2 | 2 | 2 | 100%
Test Designed Automation | 9 | 2 | 3 | 2 | 70%
Debug Testing Automation | 10 | 1 |  |  | 0%
Impliment Automation | 11 | 1 |  |  | 0%
Website Creation | 11 | 3 |  |  | 0%
Design Website Backend | 13 | 5 |  |  | 0%
Create Website Backend | 15 | 5 |  |  | 0%
Test/Debug Website Backend | 17 | 3 |  |  | 0%
Design Website Verification | 19 | 3 |  |  | 0%
Create Website Verification | 21 | 3 |  |  | 0%
Test/Debug Website Verification | 23 | 2 |  |  | 0%
Design Archive Storage Method | 25 | 4 |  |  | 0%
Create Design Archive Storage Method | 27 | 3 |  |  | 0%
Test/Debug Archive Storage Method | 29 | 2 |  |  | 0%
Design Troubleshooting | 30 | 3 |  |  | 0%
Create Troubleshooting | 32 | 2 |  |  | 0%
Test/Debug Troubleshooting | 34 | 1 |  |  | 0%
Test/Debug Whole System | 35 | 5 |  |  | 0%
Impliment System | 40 | 1 |  |  | 0%